## Sheet1
Goal | Schedule
Predict if a customer is likely to buy travel insurance using R/Python
| Task | Start Date | End Date | Status (Scheduled/In- progress/Done/Delayed)
| Work plan | 2024-02-06 | 2024-02-06 | Completed
| Mentor Session 1 | 2024-01-16 | 2024-01-16 | Completed
| Component 2 | 2024-02-07 | 2024-02-07 | In-progress
| Mentor Session 2 | 21-01-2024 | 21-01-2024 | Completed
| Component 3 | 2024-02-08 | 2024-02-08 | Delayed
Resources | Component 4 | 2024-02-09 | 2024-02-09 | Delayed
computer, access to a library, study material | Mentor Session 3 | 2024-02-04 | 2024-02-04 | Completed
| Check if all the components are completed? |  |  | All components outputs ready, CV & video are ready?
| Submit the Menternship |  |  | Check email for the feedback
| Attend the Mentor session |  |  | Resolve any queries
Constraints | Work on the feedback | 2024-02-12 | 2024-02-12 | Scheduled
1. Time | Submit the Menternship |  |  | Check email for the feedback